PRODUCT REQUIREMENTS DOCUMENT

# Delhi Urban Digital Twin

A browser-based mobility and city-scenario explorer for Central Delhi

| Field | Definition |
| --- | --- |
| Working name | Delhi Pulse Twin |
| Document version | 1.1 — 95%+ success scope lock |
| Owner | Pradyumn — Product + prototype lead |
| Pilot geography | One approximately 4 × 4 km Central Delhi study box |
| Future geography | Additional zones only after the pilot meets all acceptance gates |
| Primary surface | Desktop web; responsive read-only mobile view |
| Target build window | 10–12 weeks part-time after completion of the NCERT Parent Assistant |
| Status | Scope locked / not yet in development |

PRODUCT THESIS A credible digital twin is not “Delhi rendered in 3D.” It is a decision interface that combines place, time, evidence, and scenarios so a user can understand mobility stress and test a change.

## 95%+ delivery rule

SCOPE LOCK The MVP must launch from bundled, versioned data with no permission-controlled or live provider required. Live traffic, live buses and official planning feeds may enhance the experience, but disabling every external API must not break the complete guided demo.

## Recommended first demo

A user selects a weekday morning, sees congestion and bus movement around a Central Delhi corridor, switches on rainfall, and compares the baseline with a proposed bus-frequency or route scenario. Every layer states its source, timestamp, and whether it is observed, estimated, or simulated.

This PRD deliberately scopes the first release to a portfolio-grade, honest prototype. It does not claim municipal-grade prediction, safety-critical routing, or a complete real-time twin of Delhi NCR. The planned delivery confidence is 95–97%, conditional on preserving the scope lock and completing the first technical spike before visual production.

# 1. Executive summary

Delhi Pulse Twin will be an interactive 3D web application that turns fragmented urban datasets into a single spatial story. The locked MVP combines a pinned OpenStreetMap-derived city base, selected static bus routes, deterministic traffic and vehicle replay, bundled weather context, and two bounded “what-if” scenarios. Optional live adapters can enrich—but never determine—the launch experience.

| Decision | PRD choice | Why |
| --- | --- | --- |
| Scope | Central Delhi pilot first | Enough density and landmarks to feel real; small enough to optimize and validate. |
| Primary problem | Explain mobility stress and scenario impact | More useful and measurable than a generic 3D city showcase. |
| Primary user | Urban-planning student / analyst | Has a real need, but tolerates prototype-grade data and modelling. |
| Secondary user | Citizen / recruiter / portfolio reviewer | Needs a simple guided story and transparent evidence. |
| Rendering | Three.js/WebGL application | Interactive delivery; Blender is an asset and optimization tool, not the product runtime. |
| Data stance | Observed, estimated and simulated are visibly separated | Avoids misleading precision and builds trust. |
| Live data | Progressive enhancement, not MVP dependency | The build remains demonstrable if a live endpoint or key is unavailable. |

## North-star outcome

OUTCOME Within three minutes, a first-time user can locate a mobility hotspot, understand the signals behind it, and compare one plausible intervention against the baseline.

# 2. Product vision and principles

| Principle | Requirement |
| --- | --- |
| Decision before spectacle | Every major visual layer must answer a user question. |
| Honest uncertainty | Show source, freshness, coverage, confidence and mode: observed / estimated / simulated. |
| Progressive realism | Start with a stylized-but-geographically faithful city; add photoreal landmarks only where they aid orientation. |
| Graceful degradation | Cached or sample data must keep the demo usable when live feeds fail. |
| Performance is a feature | Target a useful first view on an ordinary laptop, not only a gaming machine. |
| Explainability | A user can inspect why a corridor is colored or why a scenario score changed. |
| Portfolio clarity | The product must expose problem framing, trade-offs, metrics and learning—not only engineering. |

# 3. Problem definition

Urban information is split across maps, static planning documents, transit feeds, weather portals and vendor dashboards. A non-specialist cannot easily relate these sources spatially or understand how a change in one system may affect another. Existing maps often show “what is where,” while planning tools require specialized GIS knowledge and polished digital twins are costly.

## Jobs to be done

When I study a corridor, help me see roads, buildings, transit, weather and movement together so I do not reconcile separate tools manually.

When I notice a hotspot, help me inspect the evidence and time window so I can decide whether it is meaningful.

When I consider an intervention, help me compare a transparent scenario with the baseline so I can discuss trade-offs.

When I view a portfolio demo, guide me through a coherent story so I can understand the product value without GIS expertise.

## Problem statement

PROBLEM Urban-planning learners and civic-data explorers lack an accessible, trustworthy way to combine Delhi’s spatial and mobility signals and test small, explainable scenarios without professional GIS software.

## Non-goals

Replacing official transport or disaster-management systems.

Predicting individual vehicle movement or exact travel time.

Providing emergency navigation or safety-critical advice.

Replicating every Delhi NCR building at photoreal quality.

Building a full transport-demand model in V1.

Calling estimated or replayed data “live.”

# 4. Users and stakeholders

| Persona | Need | Current friction | V1 value |
| --- | --- | --- | --- |
| Primary: urban-planning student / junior analyst | Explore spatial relationships and communicate a finding | GIS setup, fragmented sources, steep tools | Browser-based layers, time controls, comparison and export |
| Secondary: civic-curious resident | Understand what is happening near a familiar place | Technical dashboards and unexplained colors | Guided stories, plain-language cards, landmarks |
| Secondary: PM recruiter / interviewer | Evaluate product judgement and execution | Generic demos obscure trade-offs and outcomes | Clear problem, scoped MVP, instrumentation, honest constraints |
| Future: planner / transit operations analyst | Screen hypotheses before deeper study | Data silos and slow exploratory analysis | Scenario workspace and reproducible exports |

## Stakeholders

Product/prototype owner: prioritization, user research, analytics and narrative.

Data engineering: ingestion, normalization, caching and provenance.

3D/web engineering: tiling, rendering, interactions and performance.

Domain reviewer: validates definitions, assumptions and scenario wording.

Data providers/licensors: terms, attribution, rate limits and feed availability.

# 5. Scope and release strategy

| Capability | MVP / V1 | V1.5 | Later |
| --- | --- | --- | --- |
| Geography | One fixed ~4 × 4 km study box; 3 corridors | Second Central Delhi zone | Delhi NCR tiled coverage |
| 3D base | OSM-derived buildings/roads plus 3–5 landmark models | Improved materials and landmark pack | Procedural detail by neighborhood |
| Transit | Pinned static GTFS; 2–3 selected bus routes; deterministic replay | Authorized live positions and headway view | Multi-modal service analytics |
| Traffic | Bundled corridor traffic replay/estimates with explicit labels | Live TomTom flow where terms allow | Prediction and incident ingestion |
| Weather | Bundled baseline plus optional Open-Meteo current/forecast | Time-aligned playback and warnings | Flood/heat impact models |
| Planning | Not an MVP dependency | One curated reference overlay after rights review | Versioned plan comparison |
| Scenarios | Bus frequency and rainfall stress on selected corridors | Road closure | Calibrated multi-variable simulation |
| Exports | Screenshot + scenario summary | Shareable URL / JSON | Report builder and team workspace |

## Geographic selection criteria

Choose one recognizable approximately 4 × 4 km area with bus routes, major roads and landmarks.

Verify OSM building and road completeness before committing.

Select exactly three corridors and two or three bus routes for evaluation.

Define an explicit bounding box and preserve it in configuration so all pipelines are reproducible.

Freeze the boundary until all P0 acceptance criteria pass; new geography is a later release.

## Suggested pilot

Use one Central Delhi/New Delhi study box centered on a recognizable corridor, preferably Connaught Place toward India Gate/Kartavya Path. Include only three hero corridors and three to five orientation landmarks. Final bounds must be chosen after a two-day OSM completeness and render-performance spike.

# 6. User experience

## Primary user flow

Open the experience and load a default guided scene within the performance budget.

Choose Explore or Guided Story.

Toggle a layer: buildings, roads, transit, traffic or weather.

Move the time control; freshness and data mode update with it.

Select a corridor, bus, stop, building or zone to inspect evidence.

Open Scenario Lab and change one bounded variable.

Compare baseline vs scenario using map, KPI cards and explanation.

Save a screenshot or scenario summary with source and assumption metadata.

| Screen / state | Core elements | Acceptance intent |
| --- | --- | --- |
| Onboarding | 30-second value proposition; observed/estimated/simulated legend; performance mode | A non-GIS user understands what the product can and cannot claim. |
| Explore map | 3D viewport, layer rail, time control, search, legend, detail drawer | Core navigation remains visible without obscuring the city. |
| Object detail | Name/type, source, timestamp, related metrics, confidence | Every analytical mark is inspectable. |
| Scenario Lab | Baseline controls, one-variable changes, assumptions, Run, Reset | A scenario cannot be mistaken for a forecast. |
| Compare | Split/slider or side-by-side KPI delta; explanation | User identifies direction and magnitude of change. |
| Data status | Feed health, last refresh, cached fallback, coverage | Failure is visible and does not break the experience. |
| Export | Image plus concise summary, timestamp, sources and assumptions | Output remains truthful outside the app. |

# 7. Functional requirements

| ID | Requirement | Priority | Acceptance criterion |
| --- | --- | --- | --- |
| FR-01 | Load the fixed pilot geography and render buildings, primary roads, water and rail/metro. | P0 | Geometry aligns visually; missing layers fail independently. |
| FR-02 | Provide orbit, pan, zoom, reset view and named viewpoints. | P0 | First-time user can return to default view in one action. |
| FR-03 | Toggle layers and show a persistent legend. | P0 | Each visible analytical layer has a matching legend and state. |
| FR-04 | Search supported landmarks, stops and the three selected corridors. | P1 | Selecting a result moves camera and opens detail. |
| FR-05 | Display pinned static transit data for 2–3 selected bus routes. | P0 | Routes and stops match normalized feed entities. |
| FR-06 | Replay deterministic bus movement; use authorized live positions only as enhancement. | P0 | Replay works offline; live mode falls back automatically when stale. |
| FR-07 | Represent exactly three corridor traffic states from bundled replay/estimates. | P0 | Legend, source and data mode appear together. |
| FR-08 | Show bundled weather context and rain control; optionally refresh from Open-Meteo. | P0 | Weather mode, timestamp and geography are explicit. |
| FR-09 | Allow synchronized time-of-day replay. | P0 | All visible time-dependent layers share the displayed time context. |
| FR-10 | Inspect a selected entity in a detail drawer. | P0 | Drawer contains source, timestamp, unit and uncertainty/state. |
| FR-11 | Run a bus-frequency scenario. | P0 | Baseline is preserved; output shows affected metrics and assumptions. |
| FR-12 | Run a rainfall mobility-stress scenario. | P0 | Effect uses declared heuristic; no claim of physical flood prediction. |
| FR-13 | Compare baseline and scenario. | P0 | Changes are visually and numerically distinguishable. |
| FR-14 | Provide a guided portfolio story. | P0 | Completable in 3–5 minutes without free exploration. |
| FR-15 | Export a screenshot and scenario summary. | P1 | Export includes mode, timestamp, scope, sources and assumptions. |
| FR-16 | Show system/data health. | P0 | Unavailable, cached, stale and sample states are distinct. |

Priority legend

P0 = necessary for the portfolio MVP; P1 = strongly desired; P2 = later enhancement.

# 8. Data and API strategy

DATA RULE No source is “free” merely because its endpoint can be reached. Confirm access, terms, attribution, rate limits, geographic coverage, freshness and redistribution rights before integration.

| Layer | Preferred source | Known constraint | MVP fallback |
| --- | --- | --- | --- |
| Base geography | Pinned OpenStreetMap extract; Overpass only during data preparation | ODbL attribution; public Overpass is not a runtime dependency | Bundled GeoJSON/vector data with attribution |
| Buildings/roads/POIs | OSM geometry plus curated landmark corrections | Completeness and height tags vary | Rule-based heights clearly marked as estimated |
| Delhi buses | Pinned Delhi GTFS static; optional authorized GTFS-Realtime | Static times are approximate; realtime requires authorization | Deterministic route replay labelled replay/simulated |
| Metro | OSM lines/stations for geographic context only | Official live service data is outside MVP | Static geometry; no live-train claim |
| Weather | Bundled baseline plus optional Open-Meteo adapter | Live endpoint availability is not guaranteed | Pinned weather scenario with timestamp |
| Traffic speed | Bundled three-corridor replay/heuristic; optional TomTom adapter | Quota and licensing may change; caching may be restricted | Fixed states labelled estimated/replay |
| Planning/land use | Excluded from P0; DDA may inform a later curated overlay | Portal access does not imply bulk API or redistribution rights | No planning layer in the launch-critical path |
| Elevation | Not required for the flat pilot presentation | Adds processing and visual complexity | Flat terrain with deliberate streetscape relief |

## Provenance record required for every dataset

Provider and dataset name.

License/terms link and attribution text.

Retrieval time, source timestamp and refresh cadence.

Geographic bounds and coordinate reference system.

Observed, estimated, simulated or replay mode.

Transformation version and known quality limitations.

# 9. Technical architecture

## Recommended stack

| Layer | Locked MVP choice | Responsibility |
| --- | --- | --- |
| Application | Vite + TypeScript | Small, predictable web build without framework complexity. |
| 3D runtime | Three.js | Scene graph, camera, physically based materials, lighting, picking and animation. |
| Geographic math | Proj4js + local projected origin | Accurate coordinate conversion while keeping GPU coordinates numerically stable. |
| Spatial preparation | Python + GeoPandas + GDAL | Clip, project, validate and simplify the frozen dataset. |
| 3D asset pipeline | Blender → glTF/GLB | Create 3–5 landmarks, clean meshes, generate LODs and export runtime assets. |
| Loaders/optimization | GLTFLoader + DRACOLoader or MeshoptDecoder | Efficient compressed geometry and predictable loading. |
| Transit animation | Three.js CatmullRomCurve3 or sampled route polylines | Move replay buses accurately along normalized route geometry. |
| Post-processing | EffectComposer; restrained SSAO and color grading | Improve depth and polish without sacrificing accuracy or frame rate. |
| Data delivery | Versioned static JSON/GeoJSON/GLB first | Launch works without a backend or third-party API. |
| Optional adapters | Open-Meteo and TomTom, isolated behind interfaces | Enhance live context without affecting core completion. |
| Hosting | Vercel static deployment | Simple, reliable portfolio delivery with CDN caching. |

## Visual and geographic accuracy standard

Road centerlines, building footprints, stops and route paths originate from geographic data—not hand-drawn approximations.

Convert WGS84 coordinates through a suitable Delhi projected CRS and subtract a fixed local origin before Three.js rendering.

Use real OSM height/level tags when available; otherwise apply documented rule-based heights and mark them as estimated.

Hand-model only 3–5 orientation landmarks in Blender and align them to verified footprints, scale and north direction.

Use a restrained PBR material system, sun/sky lighting, ambient occlusion and atmospheric haze; avoid heavy bloom, neon styling or effects that hide data.

Maintain three levels of detail for hero landmarks and instanced procedural materials for ordinary buildings.

Target at least 30 FPS on an ordinary integrated-GPU laptop and 45–60 FPS on the primary test Mac in the default view.

## Visual quality acceptance

| Check | Pass condition |
| --- | --- |
| Map alignment | Roads, buildings, stops and route paths show no visible systematic offset at the three hero corridors. |
| Landmark scale | Each hero landmark matches its verified footprint and plausible real-world dimensions within the source-data tolerance. |
| Readability | Traffic, transit and scenario overlays remain distinguishable in day, evening and color-vision-deficiency tests. |
| Material consistency | Ordinary buildings share a coherent restrained palette; landmarks remain recognizable without photoreal textures. |
| Motion | Bus replay follows route geometry smoothly with no corner cutting, teleporting or frame-rate-dependent speed. |
| Performance | Default view meets the load, memory and FPS budgets before any additional visual effect is accepted. |

## Data pipeline

Acquire: pull only within configured bounds and provider limits.

Validate: schema, timestamp, coordinate range, duplicate IDs and null geometry.

Normalize: convert into canonical entities and WGS84 storage; use local projected CRS for distance/area calculations.

Transform: simplify geometry, derive tiles/LODs, compute corridor metrics and write provenance.

Snapshot: retain a replayable time-stamped dataset for demos and tests.

Serve: deliver versioned manifests and chunked spatial assets.

Render: load coarse context first, then detail by camera and layer state.

## System interfaces

| Endpoint / artifact | Purpose | Example output |
| --- | --- | --- |
| GET /manifest | Versions, bounds, modes, health and attribution | Dataset IDs, timestamps, status |
| GET /tiles/{z}/{x}/{y} | Vector or binary spatial tile | Roads/buildings/metrics |
| GET /transit/routes | Normalized routes and stops | GTFS-derived entities |
| GET /transit/vehicles | Authorized live, replay or simulated vehicles | Positions + feed timestamp + mode |
| GET /weather | Current/forecast data for pilot area | Temperature, rainfall, warnings |
| POST /scenarios | Execute a bounded scenario | Run ID, assumptions, metric deltas |
| GET /entities/{id} | Inspectable entity record | Geometry reference, properties, provenance |
| scene-manifest.json | Static asset registry | GLB/texture URLs, LODs, checksums |

## Canonical entities

Place: zone, corridor, road segment, building, landmark, stop and station.

Mobility: route, trip, vehicle observation, speed observation and incident if licensed.

Environment: weather observation, forecast and warning.

Scenario: baseline snapshot, parameter set, derived metrics, assumptions and run version.

Provenance: provider, license, retrieved_at, source_time, mode, coverage and transform_version.

# 10. Scenario design

The scenario engine is a transparent comparative model, not a predictive digital replica. V1 should prefer simple, inspectable heuristics over opaque accuracy claims.

| Scenario | Input | Illustrative method | Output |
| --- | --- | --- | --- |
| Bus frequency | Select route/corridor; increase/decrease frequency | Adjust headway; estimate wait-time change as roughly half-headway difference; recompute service intensity and accessible stops | Average wait proxy, buses/hour, population/POI reach if available |
| Rainfall stress | Rain intensity band and affected corridors | Apply declared speed/reliability penalty by road class or historical calibration if available | Travel-time index proxy, stressed segments, affected routes |
| Road closure — V1.5 | Close one segment | Re-route graph paths and compare added distance/time proxy | Diversion load proxy, affected routes, detour length |
| New bus route — later | Draw route and stops | Network accessibility comparison with simplified walking catchments | New reachable POIs/areas and overlap |

## Metric definitions

| Metric | Definition | Caveat |
| --- | --- | --- |
| Mobility Stress Index | Normalized composite of speed penalty, transit service pressure and weather impact for a corridor | Product-defined indicator; weights must be visible and versioned. |
| Service intensity | Scheduled or observed vehicles per hour on a selected corridor/route | Scheduled service is not actual service. |
| Wait-time proxy | Half of scheduled/assumed headway under evenly spaced arrivals | Not valid for irregular arrivals; label as proxy. |
| Travel-time index proxy | Scenario travel time divided by baseline travel time | Only as reliable as speed input and heuristic. |
| Coverage proxy | Area/POIs within a configured walking radius of supported stops | Does not represent actual accessibility for every user. |

## Scenario trust requirements

Scenario badge always visible.

Assumptions shown before and after Run.

Baseline dataset version locked to the scenario.

No output uses “will”; use “estimated,” “may,” or “under these assumptions.”

Reset returns exact baseline state.

Export includes parameter values and metric definitions.

# 11. Non-functional requirements

| Area | Target for V1 |
| --- | --- |
| Performance | First meaningful city view ≤5 seconds on target broadband laptop; interactive controls after ≤7 seconds; target ≥30 FPS in default view. |
| Asset budget | Initial compressed transfer target ≤15 MB; lazy-load detailed assets; texture atlases and Draco/Meshopt where appropriate. |
| Reliability | Core static demo works without live providers; one failed feed cannot crash the scene. |
| Freshness | UI exposes source timestamp and last successful refresh; stale thresholds configured per source. |
| Accessibility | Keyboard-accessible controls, high-contrast legends, text alternative to color, reduced-motion mode, readable detail panels. |
| Browser support | Latest Chrome/Edge/Safari desktop; responsive informational view on mobile; WebGL capability check. |
| Security | Secrets remain server-side; input bounds; rate limiting; dependency scanning; no arbitrary Overpass query from clients. |
| Privacy | No personal location needed in V1; coarse anonymous analytics; no individual vehicle or person tracking beyond legitimate public fleet feeds. |
| Observability | Log ingestion failures, API latency, render errors, asset load failures and scenario duration. |
| Reproducibility | Each demo can load a pinned snapshot and transform version. |

# 12. Analytics and success metrics

| Objective | Metric | Initial success threshold |
| --- | --- | --- |
| Comprehension | Users correctly explain observed vs simulated after onboarding | ≥80% in 5-user moderated test |
| Time to value | Time to identify first hotspot and its evidence | Median ≤3 minutes |
| Scenario usability | Users complete baseline → scenario → comparison without help | ≥70% |
| Trust | Users find source/time/assumptions when asked | ≥80% |
| Performance | Default scene meets load/FPS target on test laptop | ≥90% benchmark runs |
| Reliability | Guided demo completes despite live feed outage | 100% using fallback snapshot |
| Portfolio impact | Interviewers can articulate problem, user and core trade-off | Qualitative majority in feedback |

## Instrumentation events

app_loaded, webgl_capability, default_scene_ready, load_duration_bucket

guided_story_started/completed/abandoned

layer_toggled with layer and data mode

entity_selected with entity type

time_changed and playback_started

scenario_opened, parameter_changed, scenario_run, scenario_compared, scenario_reset

export_created

feed_status_seen, fallback_activated, error_encountered

## Research plan

Problem interviews with 3–5 planning/transport students and 2 civic-data users.

Clickable/wireframe test before 3D production: validate information architecture and trust labels.

Mid-build usability test on one corridor and one scenario.

Final benchmark with task completion, comprehension, performance and qualitative portfolio feedback.

# 13. Acceptance criteria for MVP

A first-time user can complete the guided story in under five minutes.

The pilot area loads with recognizable geography, selected landmarks and selectable corridors.

At least four core layers work: base city, transit, traffic/replay, and weather/scenario.

At least two scenarios work end-to-end: bus frequency and rainfall stress.

Every time-dependent layer shows timestamp, freshness and mode.

The experience remains usable with all external live endpoints disabled.

Baseline and scenario states are visually and numerically comparable.

Exports contain scope, time, data sources and assumptions.

No unlicensed imagery, tiles or data are redistributed.

Default scene passes the defined load, FPS and accessibility checks.

# 14. Delivery roadmap

| Phase | Duration | Deliverables | Exit gate |
| --- | --- | --- | --- |
| 0 — Discovery | 1–2 weeks | User interviews, pilot bounds, source/licensing matrix, OSM completeness audit, success criteria | One validated user problem and feasible data plan |
| 1 — Thin vertical slice | 2 weeks | One corridor; basic 3D; one static transit route; inspectable provenance | Map → select → evidence works end-to-end |
| 2 — MVP foundation | 3 weeks | Tiled city, layer system, time state, cached snapshots, detail drawer | Stable default experience within budget |
| 3 — Scenario Lab | 3 weeks | Bus-frequency and rainfall scenarios; baseline compare; metric definitions | Both scenarios pass truthfulness and reset tests |
| 4 — Guided story + polish | 2 weeks | Onboarding, narrative tour, landmarks, export, empty/error states | Five-minute demo succeeds without explanation |
| 5 — Evaluation and case study | 2 weeks | Usability tests, benchmark results, product decisions, demo video, case study | Measured outcomes and honest retrospective |
| Buffer | 2 weeks | Provider/API issues, optimization and fixes | Release candidate |

## Suggested first 10 build tasks

Write a one-page research plan and recruit five target users.

Audit OSM coverage for three candidate pilot bounds.

Create the data-source/licensing register and mark traffic as unresolved until verified.

Build a reproducible OSM → clipped GeoJSON → simplified asset script.

Render one corridor in Three.js with camera reset and object selection.

Add a dataset manifest and provenance drawer before adding more layers.

Import Delhi static GTFS and display one route with stops.

Create a pinned demo snapshot and offline fallback mode.

Prototype the bus-frequency calculation in a notebook or isolated service.

Test the vertical slice with users before producing landmark detail.

# 15. Risks and mitigations

| Risk | Likelihood / impact | Mitigation |
| --- | --- | --- |
| No reliable free live traffic feed | High / High | Make replay/estimated traffic a first-class MVP mode; add vendor integration only after terms and quota are confirmed. |
| Public API instability or access changes | Medium / High | Server-side adapters, cache, snapshots, health states and provider-independent schemas. |
| Scope explosion to Delhi NCR | High / High | Freeze one pilot bounding box and three corridors until acceptance criteria pass. |
| 3D performance problems | High / High | LOD, instancing, tiles, compressed glTF, texture atlases, lazy loading and low-quality mode. |
| Misleading simulation | Medium / High | Versioned assumptions, proxy labels, domain review and no predictive wording. |
| OSM incompleteness | Medium / Medium | Coverage audit; curated landmarks; estimated height rules disclosed. |
| Licensing/attribution errors | Medium / High | Dataset register, attribution component, no redistribution until terms are checked. |
| Blender pipeline consumes schedule | Medium / Medium | Use procedural extrusion for ordinary buildings; hand-model only orientation landmarks. |
| Solo-project fatigue | Medium / High | Vertical slices, weekly demos, fixed definition of done and defer visual perfection. |
| Recruiter sees only technical novelty | Medium / High | Guided story and case study lead with user problem, decisions, metrics and learning. |

# 16. Product decisions still open

| Decision | Default recommendation | Evidence needed |
| --- | --- | --- |
| Exact coordinates | One ~4 × 4 km Central Delhi box with exactly three corridors | OSM completeness, landmark density and first render benchmark |
| Optional live traffic | TomTom adapter only after the offline MVP is complete | License, Delhi coverage, quota and cache permission |
| Optional live weather | Open-Meteo adapter behind bundled weather state | Attribution, response validation and uptime |
| Primary persona | Planning student / junior analyst | Discovery interview signal |
| Scenario metric weights | Simple transparent version 0.1 | Domain review and sensitivity analysis |
| Visual style | Geographically faithful, lightly stylized PBR | Performance test and user orientation feedback |

## Go / no-go gates

| Gate | Go condition | No-go response |
| --- | --- | --- |
| After discovery | Users value combined spatial explanation; one feasible study area | Narrow problem or change primary use case |
| After vertical slice | One corridor loads, is inspectable and stays performant | Reduce asset detail or geographic bounds |
| Before live data | Terms, quota, freshness and fallback verified | Ship replay/sample mode only |
| Before portfolio launch | Guided task works, claims are accurate, metrics measured | Delay polish and fix trust/usability gaps |

# 17. Definition of done and quality checklist

Product: core user problem, target user and scenario value are visible in the experience.

Data: every layer has provenance, license status, mode and freshness.

Engineering: snapshot mode, error handling, tests and performance budget pass.

UX: legends, states, reduced motion, keyboard access and non-color cues pass review.

Scenario: assumptions and metric formulas are documented and versioned.

Portfolio: case study includes discovery evidence, rejected options, roadmap changes, measured results and limitations.

Demo: a stable hosted link, 90-second video, screenshots and reproducible build instructions exist.

# 18. Portfolio case-study narrative

| Case-study section | Evidence to show |
| --- | --- |
| Context | Why fragmented urban data makes spatial decisions hard; why Central Delhi was selected. |
| Discovery | Interview quotes/themes, user journey and the chosen decision question. |
| Product strategy | Why a narrow decision-support twin beat a city-scale visual demo. |
| Prioritization | MVP matrix and decisions to defer live traffic, NCR scale and photorealism. |
| Execution | Data pipeline, provenance design, performance trade-offs and scenario model. |
| Validation | Task completion, comprehension, load/FPS results and changed decisions. |
| Outcome | What shipped, measured results and what the next release would improve. |
| Reflection | Where estimates were used, what failed, and how scope protected delivery. |

## Resume draft — update only with measured facts

DRAFT Designed and built an interactive Central Delhi urban digital-twin prototype combining geospatial, transit, weather and mobility data in a Three.js experience; created transparent scenario comparisons, data provenance states and offline fallbacks, then validated usability and performance with target users.

# 19. Source verification notes

These sources establish feasibility, not automatic permission for every proposed use. Recheck their current terms and endpoint behavior at implementation time.

Delhi Open Transit Data documentation: https://otd.delhi.gov.in/documentation/

Confirms static GTFS files and states that real-time vehicle positions are available to authorized users through a private key. It also warns that static stop times are rough estimates based on constant speed.

OpenStreetMap Overpass API: https://wiki.openstreetmap.org/wiki/Overpass_API

Useful for bounded extraction and prototyping. Production architecture should use extracts or cached outputs rather than depending on a public shared instance.

OpenStreetMap copyright and licence: https://www.openstreetmap.org/copyright

Review attribution and ODbL obligations for the final data and presentation pipeline.

India Meteorological Department APIs: https://mausam.imd.gov.in/responsive/apis.php

Review registration, IP-whitelisting, terms, available products and resolution before selecting an adapter.

DDA GIS: https://dda.gov.in/gis

Potential planning and GIS reference. Verify whether specific layers can be downloaded, transformed and redistributed.

GTFS Realtime reference: https://gtfs.org/documentation/realtime/reference/

Use the standard schema when implementing vehicle positions or other real-time transit entities.

Three.js glTF loader: https://threejs.org/docs/#examples/en/loaders/GLTFLoader

glTF/GLB is the recommended runtime asset format for optimized Blender exports.

# 20. Appendix — requirement traceability

| Product objective | Key requirements | Metric / proof |
| --- | --- | --- |
| Understand a hotspot | FR-03, FR-07, FR-09, FR-10 | Time to first hotspot; evidence comprehension |
| Test an intervention | FR-11, FR-12, FR-13 | Scenario completion and comparison accuracy |
| Trust the result | FR-10, FR-15, FR-16 | Source/assumption findability |
| Experience a convincing city | FR-01, FR-02, FR-04 | Orientation and recognition feedback |
| Ship a resilient portfolio demo | FR-14, snapshot fallback, NFRs | Guided completion during feed outage |

## Document note

This PRD is a decision baseline. During discovery, update the target user, pilot bounds and traffic-data choice through explicit versioned decisions; do not silently expand the scope. The project becomes stronger when it demonstrates disciplined learning, not when every possible city layer is included.